## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | At first a clear project introduction was given so that the system objectives are well understood. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S1 | S1 | US-001 | After that analyzation of code requirements were done so that implementation constraints are clear. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S1 | S1 | US-001 | Then identification of required resources were done so that development can start smoothly. | MUST HAVE | GeeksForGeeks | Mentor | 3- Completed
S1 | S1 | US-001 | Then mentor guided and explained the concepts of Diarization , CBow model , Cosine-Similiarity , Skip gram etc . | SHOULD HAVE | GeeksForGeeks Medium | Mentor | 3- Completed
S1 | S1 | US-001 | After that establishig of coding standards were completed so that the codebase remains consistent and maintainable. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S2 | S2 | US-002 | After that finalization of the libraries were done for getting used so that the technology stack is stable. | MUST HAVE | VScode , whisper , | Mentor | 3- Completed
S2 | S2 | US-002 | design of the workflow of the system was completed so that the code execution is structured. | MUST HAVE | VScode | Mentor | 3- Completed
S2 | S2 | US-002 | evaluation of alternative approaches were done so that the most efficient solution is chosen. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S2 | S2 | US-002 | analyzation of advantages and disadvantages so that trade-offs are clearly understood. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S2 | S2 | US-002 | integration of Whisper library was done so that audio can be converted into clean text. | MUST HAVE | VScode | Mentor | 3- Completed
S2 | S2 | US-002 | evaluation of clean sample transcripts were done so that they are suitable for NLP processing. | MUST HAVE | VsCode | Mentor | 3- Completed
S3 | S3 | US-003 | understanding of NLP fundamentals were done so that text data can be processed correctly. | MUST HAVE | Geeks for Geeks | Mentor | 3- Completed
S3 | S3 | US-003 | implemention of text encoding techniques were done so that semantic meaning is preserved. | MUST HAVE | VScode | Mentor | 3- Completed
S3 | S3 | US-003 | sentence transformers are used so that high-quality embeddings can be generated. | MUST HAVE | VsCode | Mentor | 3- Completed
S4 | S4 | US-004 | understanding of RAG concepts were done so that retrieval-based responses can be implemented. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | resolving of technical doubts were done so that implementation blockers are removed. | SHOULD HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | completion of core coding was done so that the main system functionality works end-to-end. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | integration of the Senko library so that required processing features are available. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | Us-004 | integration of the WebRTC so that real-time call handling is supported. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | preprocessing and normalization of the calls were done so that data quality is improved. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | implemention of RAG was done so that responses are context-aware. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | building of a dashboard using streamlit was done so that system outputs can be monitored. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | fixing of bugs were done so that system stability is improved. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | updating of policy files were done so that compliance requirements are met. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | implemention of reporting functionality was done so that system results can be documented. | MUST HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | evaluation of deployment happened so that environment consistency is achieved. | COULD HAVE | No Dependeny | Mentor | 3- Completed
S4 | S4 | US-004 | Docker concepts were explained so that containerization is implemented correctly. | COULD HAVE | Geeks for Geeks | Mentor | 3- Completed
S5 | S5 | US-005 | complete documentation so that the system can be easily understood and maintained. | MUST HAVE | No Dependeny | Mentor | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 218 | 36 | 57 | 48 | 46 | 30 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction of the project | 2025-12-08 | 2025-12-09 | Debosmita Chakraborty | Project introduction & overview | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Requirement Analysis | 2025-12-09 | 2025-12-10 | Debosmita Chakraborty | Requirement analysis | Completed | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Resource Identification | 2025-12-10 | 2025-12-11 | Debosmita Chakraborty | Resource identification | Completed | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Coding Standards Definition | 2025-12-11 | 2025-12-12 | Debosmita Chakraborty | Coding standards setup | Completed | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 5 | Library and Technology Selection | 2025-12-15 | 2025-12-16 | Debosmita Chakraborty | Library selection | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 6 | Workflow and Architecture Design | 2025-12-16 | 2025-12-17 | Debosmita Chakraborty | Workflow design | Completed | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 7 | Whisper STT integration | 2025-12-17 | 2025-12-18 | Debosmita Chakraborty | Whisper STT integration | Completed | 10 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 8 | Transcript Learning | 2026-12-18 | 2026-12-19 | Debosmita Chakraborty | Transcript cleaning | Completed | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 9 | Study of NLP Fundamentals | 2025-12-22 | 2025-12-23 | Debosmita Chakraborty | Study of NLP fundamentals | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 10 | Text encoding Techniques | 2025-12-23 | 2025-12-24 | Debosmita Chakraborty | Text encoding techniques | Completed | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 11 | Sentence Transformers Implementation | 2025-12-24 | 2025-12-26 | Debosmita Chakraborty | Sentence Transformers study & implementation | Completed | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 12 | Doubt Resolution and Concept Clarification | 2025-12-26 | 2025-12-27 | Debosmita Chakraborty | Doubt resolution & concept clarification | Completed | 6 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 13 | RAG Concept Analysis | 2025-12-29 | 2025-12-30 | Debosmita Chakraborty | Study of RAG concepts and architecture | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 14 | Doubt Clarification Sessions | 2025-12-30 | 2026-01-02 | Debosmita Chakraborty | Doubt clarification & concept validation | Completed | 10 | 0 | 3 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 15 | Core Coding and Preprocessing Pipeline Development | 2026-01-05 | 2026-01-06 | Debosmita Chakraborty | Core coding & preprocessing pipeline | Completed | 20 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 16 | Library Integrations (Senko & WebRTC) | 2026-01-06 | 2026-01-07 | Debosmita Chakraborty | Senko library integration | Completed | 12 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 17 | Library Integrations (Senko & WebRTC) | 2026-01-07 | 2026-01-08 | Debosmita Chakraborty | WebRTC integration | Completed | 10 | 0 | 0 | 3 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 18 | RAG Implementation and Dashboard Development | 2026-01-08 | 2026-01-09 | Debosmita Chakraborty | RAG implementation & dashboard | Completed | 8 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 19 | Bug Fixing and Code Optimization | 2026-01-12 | 2026-01-16 | Debosmita Chakraborty | Bug fixing and error resolution | Completed | 16 | 3 | 3 | 3 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 20 | Code and Policy Updates | 2026-01-13 | 2026-01-16 | Debosmita Chakraborty | Code & policy updates | Completed | 12 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 21 | Docker Concepts and Containerization | 2026-01-19 | 2026-01-21 | Debosmita Chakraborty | Study of Docker concepts | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 22 | Docker Concepts and Containerization | 2026-01-21 | 2026-01-23 | Debosmita Chakraborty | Docker-based deployment implementation | Completed | 12 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 23 | Final Review and Documentation Cleanup | 2026-01-26 | 2026-01-27 | Debosmita Chakraborty | Preparation of technical documentation | Completed | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 24 | Final Review and Documentation Cleanup | 2026-01-27 | 2026-01-28 | Debosmita Chakraborty | Final review and documentation cleanup | Completed | 6 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Lack of clarity on project scope and technical requirements during initial phase. | Conducted requirement analysis and project discussions by our mentor to clearly define scope and expectations.
Sprint 2 | Day 7 | Difficulties in selecting appropriate libraries and deciding the optimal workflow. | Evaluated multiple libraries and approaches following our mentor and finalized the technology stack and workflow after comparison.
Sprint 3 | Day 14 | Difficulty understanding NLP concepts and encoding techniques; multiple technical doubts. | Mentor throughly guided and referred to learning resources (GeeksforGeeks, Medium) and resolved probable technical doubts through study and discussion.
Sprint 4 | Day 21 | Conceptual confusion regarding RAG implementation and related architecture. | Mentor conducted detailed study of RAG concepts and clarified doubts using guided discussions and ChatGPT support.
Sprint 4 | Day 28 | Installation difficulties while working with multiple libraries (Senko, WebRTC) and preprocessing logic.(Wheel error , MS build tools errors etc.) | Performed code testing, refined preprocessing steps, and successfully completed core coding and integrations through mentor's guidance .(Used faster-whisper to resolve wheel error and system heating conflict.)
Sprint 4 | Day 35 | Bugs in implementation, policy updates required, and reduced productivity due to holidays . | Fixed identified bugs, updated code and policies, and rescheduled tasks .
Sprint 4 | Day 42 | Limited experience with Docker and containerization concepts. | Team member Aditya guided on Docker fundamentals and implementation , then studied Docker-based deployment and implemented it successfully.
Sprint 4 | Day 49 | Ensuring completeness and clarity of project documentation. | Prepared structured and detailed documentation covering implementation, usage, and outcomes.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-12-08 | 2026-12-12 | All | Start documenting requirements clearly before coding. | Stop starting implementation without full clarity. | Continue structured workflow design and evaluation. | Finalized libraries, confirmed workflow, and stabilized the technology stack.
2 | Sprint 2 | 2026-12-15 | 2026-12-19 | All | Start comparing libraries before final selection. | Stop frequent changes in tools after finalizing stack. | Continue structured workflow design and evaluation. | Finalized libraries, confirmed workflow, and stabilized the technology stack.
3 | Sprint 3 | 2026-12-22 | 2026-12-27 | All | Start allocating dedicated time for concept learning. | Stop moving ahead with doubts unresolved. | Continue using reliable learning resources. | Referred to GeeksforGeeks and Medium and resolved technical doubts.
4 | Sprint 4 | 2026-12-29 | 2026-01-23 | All | Start incremental testing during implementation. | Stop delaying bug fixes until later phases. | Continue iterative coding and doubt-clearing sessions. | Fixed bugs, updated code and policies, completed Docker implementation despite holidays.
5 | Sprint 5 | 2026-01-26 | 2026-01-28 | All | Start incremental testing during implementation. | Stop postponing documentation to the last sprint. | Continue maintaining clear and structured documentation. | Prepared and finalized complete project documentation.
6
7